{"text_format":"3","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":7,"n_cols":8,"rows_kept":7,"merged":[[0,0,0,7],[1,0,1,7]]}
["江阴市公共资源交易中心"]
["招标代理机构开评标现场动态考评统计表（2025年7月—9月）"]
[]
["序号","招标代\n理机构","标段名称","招标人","日期","扣分\n事项","扣分分值","备注"]
[1,"江苏信中天工程咨询有限公司","江阴现代农业产业融合发展（一期）项目（排涝部分）","江阴市南郊城乡建设有限公司","2025-07-04","招标文件中系数抽取未按照无锡市水利局文件《无锡市水利工程建设项目招标投标实施办法》（锡水规[2024]1号）中的要求设置，招标文件存在重大瑕疵，导致评标工作无法进行，项目流标后重新招标。",0.5,"招标代理机构必须熟悉最新的招投标法律法规。"]
[2,"无锡苏名建设咨询有限公司","云顾路林下空间再利用工程二期（长泾段）","江阴市东舜城乡一体化建设发展有限公司","2025-08-19","招标文件3.6.5施工组织设计暗标编制要求勾选了采用，但本项目采用二合一评标法，不要求编制施工组织设计。",0.2,"招标代理机构必须熟悉系统设置与招标文件设置的一致性。"]
[3,"中招国际招标有限公司","无锡(江阴)港石利港区利港电厂3号码头改建工程EPC项目","江阴利港发电股份有限公司","2025-09-25","代理在评委抽取前未能及时与甲方、监管部门及时沟通，抽取评委时发生错误，系统设置抽取评委人数为0，导致本应该9月25日上午9点评标的项目没有评委到场，重新抽取评委后再评。",0.2,"招标代理机构必须熟悉系统的操作流程和方法。"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0}